## Deliverables
List of deliverables
Task | ID | Class | Type | Title | Target Date | Current status | Progress (finger in the air)
T083 Treebanks | T083M1 | Milestone | Document | Requirements and technical design | 2021Q3 | Not started
T083 Treebanks | T083D1 | Deliverable | Software | Scalable treebank search integrated with token-based search: backend and frontend | TBD | Not started
T083 Treebanks | T083D2 | Deliverable | Document | Scalable treebank search documentation | TBD | Not started
T124 Parallel corpora | D124M1 | Milestone | Document | Requirements and technical design | 2021Q3 | Internal discussion
T124 Parallel corpora | D124D1 | Deliverable | Software | Parallel corpus search engine: backend and frontend | 2022Q4 | Not started
T124 Parallel corpora | D124D2 | Deliverable | Document | Parallel corpus search engine: documentation | 2023Q2 | Not started
T085 Manual Annotation | T085M1 | Milestone | Document | Requirements and technical design | 2021Q2 | Internal discussion
T085 Manual annotation | T085D2 | Deliverable | Software | Manual annotation of corpus search results: backend and frontend | 2022Q4 | Not started
T085 Manual annotation | T005D2 | Deliverable | Document | Manual annotation of corpus search results:documentation | 2022Q4 | Not started
T036 Older Dutch | T036D0a | Deliverable | Document | Tagging guidelines | 2021Q1 | Nearly finished | 95
T036 Older Dutch | T036D0b | Deliverable | Document | Corpus encoding | 2021Q1 | In progress | 60
T036 Older Dutch | T036D1 | Deliverable | Document | Evaluation | 2020-2023 | Evaluation procedures being implemented in GALAHAD platform | 15
T036 Older Dutch | T036D2a | Deliverable | data | Training data | 2020-2023 | Currently working on mapping existing resources | 5
T036 Older Dutch | T036D2b | Deliverable | data | Tagged PoC corpus | 2023 | Work on TEI versions of missiven data | 0
T036 Older Dutch | T036D3 | Deliverable | Software | Tagging services/applications | 2021Q4 | In progress as part of GALAHAD platform | 60
T036 Older Dutch | T036D4 | Deliverable | Software | Environment for manual correction | 2022 | Work ongoing | 80
T036 Older Dutch | T036D5 | Deliverable | Website | Website with demonstrator tools and documentation | 2023 | Work on web application for GALAHAD platform is in progress | 30
T012 Digitisation & Conversion Infra | T012D1 | Deliverable | Software | Enhanced version of TICLL (RU) | TBD | Not started
T012 Digitisation & Conversion Infra | T012D2 | Deliverable | Software | Enhanced PICCL workflows | TBD | Not started
T012 Digitisation & Conversion Infra | T012D3 | Deliverable | Software | Enhanced and user-friendly PICCL interface | TBD | Not started
T012 Digitisation & Conversion Infra | T012D4 | Deliverable | Website | Website with demonstrator tools and documentation | TBD | Not started
T072 Tool monitoring
T026 Interoperability
T026 Interoperability
T008 Dialect dictionary curation & portal | T083D1 | Deliverable | Data, documentation | Integration of WND data model | TBD | Not started
T008 Dialect dictionary curation & portal | T083D2 | Deliverable | Software | Enhancements to DSDD portal | TBD | Not started
Deliverable descriptions
Task | ID | Class | Type | Description
T083 Treebanks | T083M1 | Milestone | Document | Document defining the requirements for the scalabale treebank search, based on input from a set of use cases.
| T083D1 | Deliverable | Software | Scalable treebank search implementation base on BlackLab and GreTeL
| T083D2 | Deliverable | Document | Document describing T083D2 and its application to use cases.
T124 Parallel corpora | D124M1 | Milestone | Document | Document defining the requirements for the BlackLab-based parallel corpus search, based on input from a set of use cases.
| D124D1 | Deliverable | Software | Parallel corpus search engine based on BlackLab and corpus fontend
| D124D2 | Deliverable | Document | Document describing D124D1 and its application to use cases.
T085 Manual Annotation | T085M1 | Milestone | Document | Document defining the requirements for the manual annotation of corpus search results, based on input from a set of use cases.
| T085D2 | Deliverable | Software | Implementation manual search result annotation, based on BlackLab and the BlackLab corpus frontend
| T005D2 | Deliverable | Document | Document describing T085D2 and its application to use cases.
T036 Older Dutch | T036D0a | Deliverable | Document | Tagging guidelines Diachronic linguistic research based on linguistically annotated texts would be better facilitated if we had a tagset applicable to all language stages of historical Dutch. The document contains a proposal for the Tagset for Diachronous corpus material of Dutch (TDN). For the determination of this tagset we have based ourselves on the tagset of GiGaNT (Groot Geïntegreerd lexicon van de Nederlandse Taal), the corpus tagset CGN/D-Coi, the tagset Corpus Gysseling, the tagset Corpus Van Reenen-Mulder, the tagset of Corpus Oudnederlands, the Nederlab project, the linguistc annotations of letters by P. C. Hooft and the historical dictionaries: the Old Dutch Dictionary (ONW) 500-1200, the Early Middle Dutch Dictionary (VMNW) 1200-1300, the Middle Dutch Dictionary (MNW) 1250-1550 and the Dutch Language Dictionary (WNT) 1500-1976. We tested the proposals by performing a complete mapping of the CGN/D-Coi tags, the tags in Corpus Gysseling and the tags in Corpus Oudnederlands to TDN.
| T036D0b | Deliverable | Document | Corpus encoding This document contains recommendations for linguistic annotation of historical texts in CLARIN-standardized formats. Our first target is a proposal for linguistic annotation in TEI P5. Further objectives are proposals for FoLiA and NAF.
| T036D1 | Deliverable | Document | Evaluation of linguistic annotation for historical Dutch The document contains evaluation results on ground truth data for state-of-the art systems tackling linguistic annotation of historical Dutch
| T036D2a | Deliverable | data | Training and evaluation data Gold standard linguistic annotated corpus material for Dutch, 1200-~1970. We aim for about 100000 tokens per century.
| T036D2b | Deliverable | data | Proof of concept corpus Linguistically annotated corpus, using the best available automatic tagging system for the material at hand. The corpus composition will be determined by use cases, a.o. those emerging from WP6.
| T036D3 | Deliverable | Software | Tagging services/applications Web application (code named 'GALAHAD') for historical enrichment of historical Dutch, designed to enable the user to chose the most fitting option from available systems. The system is designed in such a way that models/systems can easily be added by proving a docker container satisfying a specified interface.
| T036D4 | Deliverable | Software | Web-based environment for manual correction of linguistic annotation
| T036D5 | Deliverable | Website | Website with demonstrator tools and documentation
T012 Digitisation & Conversion Infra | T012D1 | Deliverable | Software | Enhanced version of TICLL (RU) The planned extensions to PICCL are described in the project plan.
| T012D2 | Deliverable | Software | Enhanced PICCL workflows The planned extensions to PICCL are describe in the project plan.
| T012D3 | Deliverable | Software | Enhanced and user-friendly PICCL interface Create a new web-based front-end for the PICCL workflow system, enabling users to – Bypass advanced options with the help of a very simple interface (cf. PhilosTEI) thatdetermines more options from the input supplied by the user – Enable simple evaluation scenarios, with uploaded ground truth or gold standard – Provide a simple demonstrator platform that allows users to assess easily how tools might work on their material
| T012D4 | Deliverable | Website | Web site with demonstrator tools and documentation
T008 Dialect dictionary curation & portal | T083D1 | Deliverable | Data, documentation
| T083D2 | Deliverable | Software
Narrative April 2021
Work has mainly concentrated on Historical Dutch, planning of corpus search extension extension modules and the WP6 use cases - Good progress on manual annotation tool for tagging/lemmatization, which will be delivered for testing to external users by the end of april - Worked on the design of the treebank extension for blacklab and elaborating requirements for the parallel extension - Work on the use case for the 17th century newspapers, both on postprocessing the part which has already been digitized and the part which still needs to be pre-OCR'd using state of the art digitization tools